## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | DIETAR
Daza, Ronnie M.
Enter Company Name in cell B2. | Domer, Jezell C. | DnD Enterprise
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Salazar, Yliza Nicole | Project Start: |  | 2023-04-12
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Santos, Sebastian | Display Week: |  | 1 |  |  | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01 | [6 empty] | 2023-05-08 | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22 | [6 empty] | 2023-05-29 | [6 empty] | 2023-06-05
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2023-04-10 to 2023-06-11
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2023-04-10 to 2023-06-11
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Tools
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Tool 1: Project Proposal | Daza, Domer | 100% | 2023-04-12 | 2023-04-12 | 1
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Research | All Members | 0% | 2023-04-12 | 2023-04-30 | 19
| Tool 2: Gantt Chart | Jezell Domer | 100% | 2023-04-26 | 2023-04-27 | 2
| Tool 3: Initial Project Charter | Daza, Domer | 100% | 2023-04-27 | 2023-05-02 | 6
| Tool 4: Flow Chart | Ronnie Daza | 100% | 2023-04-26 | 2023-04-28 | 3
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Tool 5: UI Layout Design / Project Prototype | All Members | 100% | 2023-04-30 | 2023-05-10 | 11
| Tool 6: UML | Daza, Domer | 100% | 2023-04-30 | 2023-05-10 | 11
| Tool 7: Work Breakdown Structure | Daza, Domer | 100% | 2023-04-28 | 2023-05-10 | 13
| Tool 8: Test Cases | Jezell Domer | 100% | 2023-05-10 | 2023-05-14 | 5
| Tool 9: Src code |  | 0% | 2023-05-20 | 2023-07-18
| Trello | All Members | 100% | 2023-04-26 | 2023-04-26 | 1
Sample phase title block | User Profile
| User Log-In | Salazar | 20% | 2023-06-11 | 2023-06-16 | 6
| User Profile Edit |  | 0% | 2023-06-17 | 2023-06-27 | 11
| User Profile Delete |  | 0% | 2023-06-18 | 2023-06-27 | 10
| Skip Profile Creation |  | 0% | 2023-06-19 | 2023-06-27 | 9
Sample phase title block | App Menu / Features
| BMI Button |  | 0% | 2023-06-10 | 2023-06-20 | 11
| Diet Plan |  | 0% | 2023-06-11 | 2023-06-20 | 10
| Workout Plan |  | 0% | 2023-06-12 | 2023-06-20 | 9
| Journal |  | 0% | 2023-06-13 | 2023-06-20 | 8
| Exit / Quit |  | 0% | 2023-06-14 | 2023-06-20 | 7
Sample phase title block | Monetization
| Partnerships |  | 0% | 2023-06-16 | 2023-06-17 | 2
| In-App Advertising |  | 0% | 2023-06-17 | 2023-06-19 | 3
Testing
| Testing User Log-in |  | 0% | 2023-06-20 | 2023-06-25 | 6
| Testing Functions |  | 0% | 2023-06-25 | 2023-06-30 | 6
| Debug |  | 0% | 2023-06-20 | 2023-07-10 | 21
| App Release / Playstore |  | 0% | 2023-07-11 | 2023-07-23 | 13

## Sheet1
Project Name: |  | Caloriesify
Created by: |  | Daza, Domer, Salazar, Santos
Date of Creation: |  | 2023-05-10
Date of Review:
TEST CASE ID | TEST SCENARIO | TEST CASE | PRE-CONDITION | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS (PASS/FAIL)
OPEN_001 | Making sure that the app is starting | Launch the application and ensure that the homepage is displayed correctly. | Must be downloaded and installed. | 1. Launch the application from the device's home screen. | Launched | • The application should open without any errors or crashes. • The user interface should be displayed correctly and contain all the necessary options and buttons. | The app launced and run succesfully | Pass
|  |  |  | 2. Verify that the application opens without any errors or crashes. | No errors and crashes
3. Verify that the main menu or home screen contains all the options and buttons for the application's functionality.
LOG-IN_001 | Verify that the user can log in to the application successfully | Enter Valid User Name and Valid Password | Need a valid Gmail Account to Log-in | 1. Enter a valid email address and password in the appropriate fields. | Email: jezelldomer@gmail.com Password: ****** | • Successful Log-in • The user's name or profile picture should be displayed correctly on the user profile management | Can't Log-in or Sign-up, back-end is not yet finish There are some minor errors in the front-end. Cannot see the welcome and login messages, and there are overlay problems. | Fail
|  |  |  | 2. Verify that the user is redirected to the application's dashboard or home screen. | Username: Jezell
3. Verify that the user's name or profile picture is displayed on the dashboard or home screen.
BMI_001 | App will ask users to input their BMI | Verify that the application can correctly calculate the user's BMI based on the entered height and weight. | Must enter their latest weight and height, age, and target weight. | 1. Enter a valid height in meters and weight in kilograms in the appropriate field. | 5 ft 3 inches and 42 kg | • The BMI value should be classified as normal, overweight, underweight or obese according to BMI classifications. | Can input informations, then tried to save and proceed. It loaded and analyzed, but the information was not saved in the account settings, and the BMI result was not displayed. | Fail
|  |  |  | 2. Enter age in the appropriate field. | 20
3. Verify that the calculated BMI value is displayed correctly.
EXER_001 | App will generate exercise plan | Verify that the application can generate exercise plans based on the user's calculated BMI. | The app must calculate the BMI of the user first | 1. Verify that the exercise plan generated by the application is appropriate for the user's BMI classification. |  | • The exercise plan generated by the application should be based for the user's BMI classification. • The application should correctly generate exercise plans for different input values.
2. Verify that the exercise plan contains exercises that are safe and effective for the user's fitness level and health status.
3. Verify that the exercise plan is easy to understand and follow.
DIET_001 | App will generate diet plan | Verify that the application can generate diet plans based on the user's calculated BMI. | The app must calculate the BMI of the user first | 1. Verify that the diet plan generated by the application is appropriate for the user's BMI classification. |  | • The diet plan generated by the application should be appropriate for the user's BMI classification. • The diet plan should contain foods that are nutritious and appropriate for the user's dietary needs and restrictions.
2. Verify that the application has saved the new entry.
3. Verify that the reaction button has different emoji options to choose from and verify that the selected emoji is displayed next to the new entry.
JOURNAL_001 | Users can take notes their progress everyday | Verify that the application can save user notes and track their progress. | Must input notes and then save to check if it's actually saved. | 1. Enter a valid title for the new entry and enter a valid note in the text field. |  | • The application should save the new entry correctly and without any errors. • The user should be able to view their previously saved notes and entries and the reaction button should have different emoji options to choose from and the selected emoji should be displayed next to the new entry.
2. Enter a valid weight in kilograms in the appropriate field.
3. Verify that the calculated BMI value is displayed correctly.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.